## Slide 1
ConnectWise Keka Integration
Project Planning & Status Update
* * *
As of June 10, 2026
OculusIT
RISK FLAG
Keka API dependencies must be enabled by June 12th. Delay = Project release at RISK.

## Slide 2
OculusIT
Executive Summary
June 10, 2026
Overall Project Health: AMBER — On track technically; external API dependency creates release risk
4 of 5
Phases Completed / Active
June 30
Target Release Date
June 12
Critical API Deadline
0
Open Blockers (tech)
Key Highlights
Development is on track — all technical activities completed through this week.
Phase 1 (PSA Sync) and Phase 2 (Timesheet Sync) implementations are complete.
Some Keka API fields required for this release are not yet exposed by Keka.
If Keka API dependencies are not enabled by June 12th, the June 30th release is at RISK.
Failure / negative use cases for Phase 1 are fully addressed.

## Slide 3
OculusIT
Phase Status Overview
June 10, 2026
Phase
Status
Target Date
Comments
Foundation / Discovery Phase
Completed
May 11, 2026
All observations tracked and planned into Implementation Phase
Implementation Phase 1 PSA Synchronization
Completed
May 15, 2026
Some fields not yet exposed by Keka API — noted as dependency
Implementation Phase 2 Timesheet Synchronization
Completed
June 5, 2026
Majority of functionality complete; placeholders added for API gaps
Fix Dependencies & Bugs (Phase 1 & Phase 2)
Not Started
June 18, 2026
Projects, Timesheets, Companies — pending Keka API enablement
Technical — Negative / Failure Use Cases (Phase 1)
Completed
June 1, 2026
Completed through Phase 1
Release Phase
Not Started
June 30, 2026
E2E testing, QA Sign-Off, UAT Sign-Off, Production Release & Support

## Slide 4
OculusIT
Project Timeline
May — June 2026
May 2026
June 2026
W1
W2
W3
W4
W1
W2
W3
W4
Apr28
May4
May11
May18
May25
Jun1
Jun8
Jun15
Foundation / Discovery
Done May 11
Impl Phase 1 - PSA Sync
Done May 15
Impl Phase 2 - Timesheet
Done Jun 5
Negative/Failure Cases P1
Done Jun 1
Fix Dependencies & Bugs
Target Jun 18
Release Phase
Target Jun 30
Today Jun 10
API Deadline Jun 12
Completed
Not Started
Today (Jun 10)
API Deadline (Jun 12)

## Slide 5
OculusIT
Risk & Dependency Analysis
RISK: Keka API dependencies not enabled by June 12th will delay the June 30th production release.
Risk Details
Risk ID
R-001
Risk Owner
Keka Platform Team
Deadline
June 12, 2026
Impact
Phase fix & Release phases blocked
Probability
High — API not confirmed yet
Severity
High — affects June 30 go-live
Current Status
Open / Awaiting Keka response
Mitigation Plan
Immediate Action
Escalate to Keka account manager — request written confirmation of June 12th API enablement.
Parallel Track
Continue development with placeholder stubs. All code is ready to switch once APIs are live.
Contingency
If APIs are delayed beyond June 12th, revise release date and notify all stakeholders within 24 hrs.
Monitoring
Daily check-in with Keka team from June 10th. Status updated in project tracker same day.

## Slide 6
OculusIT
Phase Details
01
Foundation / Discovery
Completed
May 11, 2026
Studied ConnectWise, Keka and AWS infrastructure
Built POC: initial Customers sync integration
Identified gaps between ConnectWise and Keka data models
Designed and reviewed the Integration System architecture
All observations documented and fed into Phase 1 planning.
02
Implementation Phase 1 PSA Synchronization
Completed
May 15, 2026
Implemented Customers (Companies) sync CW -> Keka
Implemented Projects sync CW -> Keka
Resolved initial data-model gaps identified in Discovery
Some Keka API fields required for release are not yet exposed.
03
Implementation Phase 2 Timesheet Synchronization
Completed
June 5, 2026
Implemented full Timesheet sync ConnectWise -> Keka
Hourly incremental sync with duplicate prevention
Audit-trail rejection detection added
Placeholders added where Keka API is not yet available
Majority of functionality complete. Pending API enablement.
04
Fix Dependencies & Bugs Phase 1 & Phase 2
Not Started
June 18, 2026
Projects, Timesheets, Companies — final bug fixes
Close all API-dependency placeholders once Keka enables fields
Regression testing across all sync flows
Blocked until Keka API fields are enabled (deadline: Jun 12).
05
Negative / Failure Use Cases Phase 1 Technical
Completed
June 1, 2026
Error handling for API failures and timeouts
Retry logic and circuit-breaker patterns
Partial-failure scenarios for company and project sync
Completed through Phase 1. Phase 2 patterns follow same design.
06
Release Phase
Not Started
June 30, 2026
End-to-end integration testing across all flows
QA sign-off and UAT sign-off
Production deployment and smoke test
Post-release production support window
Dependent on successful close of all dependency issues.

## Slide 7
OculusIT
What's Next — Action Items
Immediate priorities to keep the June 30 release on track
URGENT
Jun 10–12
Keka API Enablement
Confirm with Keka team that required API fields will be enabled by June 12th. Escalate to account manager if no confirmation received by EOD June 11th.
HIGH
Jun 12–18
Fix Dependencies & Bug Fixes
Once Keka APIs are live, close all placeholder implementations in Phase 1 & Phase 2. Run regression tests across Companies, Projects and Timesheet sync flows.
HIGH
Jun 12–18
Phase 2 Failure Use Cases
Implement negative / failure use cases for Timesheet Synchronization (mirroring patterns already done for Phase 1).
MEDIUM
Jun 18–25
End-to-End Integration Testing
QA team to execute full E2E test suite covering all sync flows. Track and resolve any defects before UAT sign-off.
MEDIUM
Jun 25–28
UAT Sign-Off
Business stakeholders to validate data accuracy in Keka against ConnectWise. Obtain formal UAT sign-off document.
PLANNED
Jun 30
Production Release
Deploy to AWS ECS Fargate production environment. Monitor first 3 sync runs. Production support window begins.

## Slide 8
Questions & Discussion
We welcome any questions on the plan, risks or timeline.
Project
ConnectWise Keka Integration
Release Target
June 30, 2026
Critical Date
June 12, 2026 (Keka API deadline)
Health
AMBER — API dependency risk open
Thank you
OculusIT | Project Planning | June 10, 2026